## OFM Phase 1
Item | BID UNITS | ID ON DWGS. |  | Chugach | Manufacturer/ | Approximate | Total |  | Required | Unit | Extended | Status/Delivery | Delivered to
|  |  | Description | ID No. | Part Number | Weight, lbs. | Approx. Weight | Unit | Quantity | Price | Price | Date | Site by
FDN. PIPE
1 | PP24x4-35 |  | 24" OD, 1/2" WALL, 35' LONG |  | MVA POWER | 4410 | 13230 | ea. | 3 | 8342.8 | 25028.4 | Delivery by: 2/4/2025 | Contractor
2 | PP30x5-35 |  | 30" OD, 5/8" WALL, 35' LONG |  | MVA POWER | 6860 | 13720 | ea. | 2 | 12999.8 | 25999.6 | Delivery by: 2/4/2025 | Contractor
STEEL POLE STRUCTURES
3 | ITIN 1-2 60' |  | 60' ITIN 1-1 STEEL POLE STRUCTURE |  | VALMONT | 7524 | 15048 | ea. | 2 | 23319 | 46638 | Delivered by: 12/16/2024 | Contractor
4 | N-1 27.5' |  | 27.5' N-1 STEEL STUB POLE STRUCTURE |  | VALMONT | 2764 | 2764 | ea. | 1 | 8682 | 8682 | Delivered by: 12/16/2024 | Contractor
5 | N-4 29' |  | 29' N-4 STEEL H-FRAME STRUCTURE |  | VALMONT | 6770 | 6770 | ea. | 1 | 21326 | 21326 | Delivered by: 12/16/2024 | Contractor
INSULATORS
6 | STM-3B | 1 | INSULATOR, HORIZONTAL POST, 2.5" ROD, 61", FLAT BASE, 2-HOLE BLADE, 138kV |  | MACLEAN #H21010050MXSS026 |  |  | ea. | 6 | 470.5 | 2823 | Delivered: 12/13/2024 | Contractor
7 | STM-10, STM-10D | 2 | INSULATOR, SUSPENSION, Y-CLEVIS BALL, 138kV, 25K |  | MACLEAN #S14080048MXSS024 |  |  | ea. | 12 | 144.6 | 1735.2 | Delivered: 10/29/2024 | Contractor
8 | STM-10S | 3 | INSULATOR, SUSPENSION, SOCKET BALL, 35kV, 15K | 3317 | HUBBELL #4050031301 |  |  | ea. | 6 | 20.1476 | 120.8856 | IN STOCK | Contractor
9 | STM-3F, STM-3FX | 4 | INSULATOR, VERTICAL POST, 35kV, CLAMP TOP, STUD BASE | 3304 | LAPP #510035 |  |  | ea. | 3 | 139.8366 | 419.5098 | IN STOCK | Contractor
HARDWARE
10 | STM-10 | 5 | LINK, EXTENSION, 10", Y-CLEVIS CLEVIS, 30K |  | MACLEAN #YCCHL-65 |  |  | ea. | 12 | 6923 | 83076 | Delivered:12/11/2024 | Contractor
11 | STM-10, STM-10S | 6 | SOCKET CLEVIS, 30K | 18232 & 19839 | HUBBELL #SC-30 |  |  | ea. | 18 | 51.7439 | 931.3902 | ORDERED STOCK | Potelcom
12 | STM-10, STM-10S | 7 | ANCHOR SHACKLE, 30K | 955 | HUBBELL #AS-25 |  |  | ea. | 18 | 10.7197 | 192.9546 | ORDERED STOCK | Potelcom
13 | STM-10S | 8 | Y-CLEVIS BALL | 948 | HUBBELL #HYBC-30 |  |  | ea. | 6 | 10.84 | 65.04 | ORDERED STOCK | Potelcom
14 | STM-3F, STM-3FX | 9 | INSULATOR STUD, 3/4" SHORT SHANK W/HARDWARE | 3813 | LAPP #301614 |  |  | ea. | 3 | 1.4995 | 4.4985 | IN STOCK | Contractor
15 | STM-10 | 10 | DEADEND, COMPRESSION, SINGLE TONGUE, 795 ACSR "DRAKE" |  | DMC #DC99-188-40 |  |  | ea. | 12 | 278 | 3336 | Delivered: 12/9/2024 | Contractor
16 | STM-10S | 11 | DEADEND, COMPRESSION, 795 AAC "ARBUTUS" |  | DMC #DB99-188-25 |  |  | ea. | 6 | 188.75 | 1132.5 | Delivered: 12/9/2024 | Contractor
17 | STM-3F, STM-3FX | 12 | TRUNNION CLAMP, 1.00" - 1.50" CLAMPING RANGE | 803 | LAPP #47114 |  |  | ea. | 3 | 8.1836 | 24.5508 | IN STOCK | Contractor
18 | STM-3B | 13 | JUMPER CLAMP, 795kcmil ACSR "DRAKE" | 18977 | HUBBELL #97642-3002 |  |  | ea. | 6 | 286 | 1716 | ORDERED STOCK | Potelcom
19 | STM-10D | 15 | DEADEND, COMPRESSION, DOUBLE TONGUE, 795 ACSR "DRAKE" | 19818 | HUBBELL #A021245 |  |  | ea. | 3 | 155.88 | 467.64 | IN STOCK | Contractor
GUY MATERIALS
20 | TG-21D-2FG | 7 | ANCHOR SHACKLE, 30K | 955 | HUBBELL #AS-25 |  |  | ea. | 18 | 21 | 378 | ORDERED STOCK | Potelcom
21 | TG-21D-2FG | 25 | GUY STRAIN INSULATOR, 30K, 42", CLEVIS-CLEVIS W/2 ROLLERS |  | MACLEAN #GCC30-42R2 |  |  | ea. | 9 | 72.72 | 654.48 | ORDERED STOCK | Potelcom
22 | TG-21D-2FG | 26 | GUY STRAIN INSULATOR, 30K, 42", CLEVIS-CLEVIS W/1 ROLLER |  | MACLEAN #GCC30-42R |  |  | ea. | 9 | 72.72 | 654.48 | ORDERED STOCK | Potelcom
23 | TG-21D-2FG | 27 | PREFORMED GRIP FOR 25M ALUMOWELD | 876 | PREFORMED #AWDE-4130 |  |  | ea. | 36 | 21.0097 | 756.3492 | IN STOCK | Contractor
24 | TG-21D-2FG | 28 | THIMBLE CLEVIS, 30K, 5/8" PIN | 954 | MACLEAN #FSA-88A-5 |  |  | ea. | 9 | 19.9812 | 179.8308 | IN STOCK | Contractor
25 | TG-21D-2FG | 29 | GUY WIRE, 25M ALUMOWELD | 5158 |  |  |  | ft. | 400 | 1.47 | 588 | IN STOCK | Contractor
CONDUCTOR ACCESSORIES
26 | 138KV RELOCATE |  | SPLICE, COMPRESSION, FULL TENSION FOR 795kcmil "DRAKE" ACSR | 4494 | HUBBELL #A151245 |  |  | ea. | 6 | 224.2864 | 1345.7184 | IN STOCK | Contractor
27 | 138KV RELOCATE |  | ARMOR RODS FOR 795 ACSR "DRAKE" | 7165 | PREFORMED #AR-0141 |  |  | ea. | 6 | 55.0272 | 330.1632 | IN STOCK | Contractor
28 | 35KV RELOCATE |  | SPLICE, COMPRESSION, FULL TENSION FOR 795kcmil "ARBUTUS" AAC |  | DMC #DB96-188-25 |  |  | ea. | 3 | 67.9 | 203.7 | Delivered: 12/9/2024 | Contractor
CONDUCTOR
29 | 138KV RELOCATE |  | 795 KCMIL ACSR, "DRAKE" | 1237 |  |  |  | ft. | 300 | 3.1781 | 953.43 | IN STOCK | Contractor
30 | 35KV RELOCATE |  | 795 KCMIL AAC, "ARBUTUS" | 1245 |  |  |  | ft. | 50 | 1.9395 | 96.975 | IN STOCK | Contractor
[10 empty] | MATERIAL TOTAL = | 229860.2961